## Trang_tính1
Tasks Name | Start Build | Finish Build | % Build | Names | Start Testing | Finish Testing | % Testing | Names | Notes
users(deleteUser,banUser,unBanUser,setPermission,getAllUser,getUserPageDivision) | 15/3/2023 | 16/3/2023 | 100% | Nguyễn Trí Hậu | 16/3/2023 | 16/3/2023 | 100% | Đỗ Thịnh
movies(updateMovie,deleteMovie,getMovieByName) | 17/3/2023 | 20/3/2023 | 100% | Nguyễn Trí Hậu | 20/3/2023 | 20/3/2023 | 100% | Đỗ Thịnh
cinemas(createCinemaSystem,deleteCinemaSystem,getCinemaSystem,createCinemaComplex,deleteCinemaComplex,getCinemaComplex) | 21/3/2023 | 24/3/2023 | 100% | Nguyễn Trí Hậu | 24/1/2022 | 24/3/2023 | 100% | Đỗ Thịnh
data(getSeatByCinema,updateSeat,getShowTimeByMovie,getSeatByShowTime) | 24/3/2023 | 26/3/2023 | 100% | Nguyễn Trí Hậu | 26/1/2023 | 26/3/2023 | 100% | Đỗ Thịnh
admin | 26/3/2023 | 26/3/2023 | 50% | Nguyễn Trí Hậu | 26/1/2023 | 26/3/2023 | 100% | Đỗ Thịnh
order(getCurrentOrder,deleteOrder,getOrderByShowTime) | 27/3/2023 | 28/3/2023 | 100% | Nguyễn Trí Hậu | 28/1/2023 | 28/3/2023 | 100% | Đỗ Thịnh
permission | 29/3/2023 | 29/3/2023 | 50% | Nguyễn Trí Hậu | 29/2/2023 | 29/3/2023 | 100% | Đỗ Thịnh
users(signup,signin,getCurrentUserInfo,updateUser,getUserByName) | 15/3/2023 | 16/3/2023 | 100% | Đỗ Thịnh | 16/3/2023 | 16/3/2023 | 100% | Nguyễn Trí Hậu
movies(create,getMovieInfo,getBanner,getMovieByDate) | 17/3/2023 | 20/3/2023 | 100% | Đỗ Thịnh | 20/3/2023 | 20/3/2023 | 100% | Nguyễn Trí Hậu
cinemas(createCinema,deleteCinema,getCinemaInfo,getCinemaByComplex,updateCinema) | 21/3/2023 | 24/3/2023 | 100% | Đỗ Thịnh | 24/1/2022 | 24/3/2023 | 100% | Nguyễn Trí Hậu
data(createShowTime,deleteShowTime,getShowTime,createSeat,deleteSeat) | 24/3/2023 | 26/3/2023 | 100% | Đỗ Thịnh | 26/1/2023 | 26/3/2023 | 100% | Nguyễn Trí Hậu
admin | 26/3/2023 | 26/3/2023 | 50% | Đỗ Thịnh | 26/1/2023 | 26/3/2023 | 100% | Nguyễn Trí Hậu
order(order,adminCreate) | 27/3/2023 | 28/3/2023 | 100% | Đỗ Thịnh | 28/1/2023 | 28/3/2023 | 100% | Nguyễn Trí Hậu
permission | 29/3/2023 | 29/3/2023 | 50% | Đỗ Thịnh | 29/2/2023 | 29/3/2023 | 100% | Nguyễn Trí Hậu